## Slide 1: EYDP Early Years Digital Portfolio
Second Partners’ Meeting
Florence, 6 – 7 March 2023
Project number
2022-1-PT01-KA220-SCH-000086979

## Slide 2
The European Commission's support for the production of this presentation does not constitute an endorsement of the contents, which reflect the views only of the authors, and the Commission cannot be held responsible for any use which may be made of the information contained therein.
Funding Programme
Open Education Resources License

## Slide 3: Context
The motivation that backs up the “Early Years Digital Portfolio” EYDP project is related to the challenge felt by early childhood educators and kindergarten teachers in performing appropriate documentation and evaluation of the learning progresses in early childhood education and in cooperating with the families on the matter.
Early childhood educators and kindergarten teachers do not feel sufficiently prepared and motivated to provide appropriate visibility of the children's learning process to be shared with their families.

## Slide 4: Objectives
Create a more effective and transparent communication pattern among childhood education and care systems and families.
Provide childhood educators and kindergarten teachers with:
Pedagogical and methodological approaches to improve their evaluation and documentation skills integrating children and families in the process.
The skills to develop digital portfolios to document and assess the children's learning and performance.
A Digital Portfolio Management System (DPMS) that will be made accessible through the EYDP project internet portal as a web-based application.

## Slide 5: Target Groups
Kindergarten teachers
Early childhood educators
Kindergarten managerial staff

## Slide 6: Results
1
Handbook for Children Documentation and Assessment
to support the professional development of childhood educators and kindergarten teachers
2
Online Training Package
for kindergarten teachers to use digital portfolios for children learning path assessment
3
Digital Portfolio Management System
to establishing a fruitful communication pattern with families regarding the cognitive achievements of children

## Slide 7
 | 2022 | 2023 |  |  |  |  |  | 2024 |  |  |  |  |  | 2025 |  |  |  |  | 
 | 12 | 1-2 | 3-4 | 5-6 | 7-8 | 9-10 | 11-12 | 1-2 | 3-4 | 5-6 | 7-8 | 9-10 | 11-12 | 1-2 | 3-4 | 5-6 | 7-8 | 9-10 | 11
WP1 - Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP2 - Handbook |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP3 - Online Training Package |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP4 - Digital Portfolio Management System |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP5 - Valorization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Gantt chart

## Slide 8: WP2 - Handbook for Children Documentation and Assessment

## Slide 9
Activities and Results
Activities | Results
1 – Planning of the activities | Availability of: Calendar of activities Templates and tools Questionnaire in English and in national languages
2 – Needs analysis | 1 participant per partner in the transnational meeting Collection of 50 questionnaires per country (100 in Portugal) Availability of 4 national needs analysis reports Availability of 1 transnational needs analysis report 6 dimensions analysed
3 – Creation of Handbook syllabus and structure | Availability of the syllabus of the handbook
4 – Creation of Chapters contents | Production of the draft contents for 5 chapters
5 – Revision, finalization and translation of Handbook contents | Peer Review of the contents of the handbook Final version of the contents of the handbook Availability of the handbook in the 4 partner languages
6 – Testing activities and evaluation and validation of the consistency of the contents | Testing of the handbook with 20 childhood educators and kindergarten teachers per country (40 for Portugal) Availability of 4 national evaluation reports Availability of 1 transnational evaluation report
WP2 - Handbook for Children Documentation and Assessment

## Slide 10: 1 – Planning of the activities
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) should create a working group involving in the contents creation:
  The director or a representative of the managerial staff who will ensure that the handbook contents are recognised and accepted by the kindergarten
  5 Early childhood educators who will have an active role in supporting the experts of IPB, ULS and in adapting the pedagogic and methodological contents to the specific needs of educators
  Template: WP2.L – Working Group involvement declaration
IPB (PT) and ULS (IE) should create a working group involving 4 experts/lecturers/researchers in the contents creation
Template: WP2.L – Working Group involvement declaration
WP2 - Handbook for Children Documentation and Assessment

## Slide 11: 1 – Planning of the activities
Each partner should perform a preliminary needs analysis in the partner countries assessing how kindergarten teachers document and evaluate the children and what knowledge they have about pedagogical documentation.
Each partner should collect at least 50 questionnaires from kindergarten teachers and earlychildhood educators.
Template: WP2.A - Questionnaire
WP2 - Handbook for Children Documentation and Assessment

## Slide 12: 2 – Needs analysis
Each partner should produce a national needs analysis report covering 6 dimensions:
  Sociodemographic characterization of the respondents
  Conceptions about documentation and assessment
  Documentation and assessment practices
  Knowledge about pedagogical documentation and Portfolios;
  Difficulties in the child documentation and assessment process
  Needs in the child documentation and assessment process.
Templates: WP2.B - Table of Contents for national reports
WP2.C - Guidelines for the national report production
Each partner should participate in the Partners’ Meeting in Florence on:
6 – 7 March 2023
IPB (PT) and ULS (IE) should produce a transnational needs analysis report
WP2 - Handbook for Children Documentation and Assessment
Partner | Needs Analysis National Report
Italy | OK
Ireland | OK
Portugal | 
Romania | OK

## Slide 13: 3 – Creation of Handbook syllabus and structure
IPB (PT) and ULS (IE) should propose the handbook syllabus and structure
  Templates: WP2.D - Table of Contents for handbook
  WP2.E - Guidelines for the handbook production
Each partner should analyze and give feedback related to the handbook syllabus and structure
IPB (PT) and ULS (IE) should produce the final version of the handbook syllabus and structure
WP2 - Handbook for Children Documentation and Assessment

## Slide 14: 4 – Creation of Chapters contents
IPB (PT) and ULS (IE) should propose the contents of the 5 chapters of the handbook:
  Chapter 1: The concept of pedagogical documentation in childhood education
  Chapter 2: Relationship between pedagogical documentation and children's learning
  Chapter 3: Participatory Pedagogies in Childhood Education
  Chapter 4: Holistic approach
  Chapter 5: Ethical principles in pedagogical documentation
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) should contribute to the adaptation of the handbook contents to childhood education professionals
WP2 - Handbook for Children Documentation and Assessment

## Slide 15: 5 - Finalization of the Handbook contents
IPB (PT) and ULS (IE), on the documents and suggestions provided by the kindergartens, should produce the final version of the handbook
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) should translate the handbook in the national languages
WP2 - Handbook for Children Documentation and Assessment

## Slide 16: 6 – Testing activities and evaluation
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) should involve 20 among kindergarten teachers and earlychildhood educators in the assessment of the handbook and produce a national evaluation report.
Templates: WP2.F – Evaluation Questionnaire
WP2.G – Tool for questionnaire analysis
WP2.H – Guidelines for evaluation report
WP2.I – Target Group involvement declaration
WP2 - Handbook for Children Documentation and Assessment

## Slide 17
Actions and Deadlines
Action | Deadline | Status
IPB (PT), Pixel (IT) Creation of the templates needed for carrying out the activities | 30 November 2022 | Completed
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) Provide IPB with feedback on the questionnaire | 19 December 2022 | Completed
IPB (PT) Provide Pixel with the final version of the questionnaire | 22 December 2022 | Completed
Pixel Creation of the English online version of the questionnaire | 22 December 2022 | Completed
IPB (PT) Produce the template for the national report | 16 January 2023 | Completed
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) Translation of the questionnare in national language and collection of 50 filled-in questionnaires | 31 January 2023 | Completed
WP2 - Handbook for Children Documentation and Assessment

## Slide 18
Actions and Deadlines
Action | Deadline | Status
IC Sestini (IT), EuroEd (RO), ULS (IE) Production of the national needs analysis reports | 28 February 2023 | Completed
IPB (PT), ULS (IE) Definition of the proposal of the table of contents for the handbook | 28 February 2023 | Completed
IPB (PT) Production of the national needs analysis reports | 16 March 2023 | 
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) Provide IPB and ULS with examples of National policy requirements and suggestions for participatory pedagogies | 16 March 2023 | 
IPB (PT) Send 4 needs analysis reports with the final layout | 20 March 2023 | 
IPB (PT), ULS (IE) Definition of the final version of the table of contents for the handbook | 31 March 2023 | 
WP2 - Handbook for Children Documentation and Assessment

## Slide 19
Actions and Deadlines
Action | Deadline | Status
IPB (PT) Production of the transnational needs analysis reports | 14 April 2023 | 
IPB (PT), ULS (IE) Definition of the draft version of the contents for the handbook | 15 June 2023 | 
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) Send feedback related to the contents of the handbook | 30 June 2023 | 
IPB (PT), ULS (IE) Definition of the final version of the contents for the handbook | 31 July 2023 | 
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) Translation of the handbook in the national languages | 30 September 2023 | 
WP2 - Handbook for Children Documentation and Assessment

## Slide 20
Actions and Deadlines
Action | Deadline | Status
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) Collect 20 evaluation questionnaires from the representatives of the target groups Sending of the National Testing Report | 31 December 2023 | 
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE), IPB (PT) Send the declaration of the target groups involvement | 31 December 2023 | 
Pixel (IT) Production of Transnational Testing Reports | 31 January 2024 | 
WP2 - Handbook for Children Documentation and Assessment

## Slide 21: WP3 - Online Training Package

## Slide 22
Activities and Results
Activities | Results
1 - Planning the activities | Availability of: Calendar of activities Templates and tools 1 participant per partner in the transnational meeting
2 – Organization of the Training activity | Logistic organization of the training activity in Romania Participation of at least 5 teachers per partner, but Pixel and IPB Involvement of 3 experts by IPB in the training Availability of: List of Participants Reports on the training activity
3 – Definition of the online course syllabus and structure | Availability of the online course syllabus
4 – Creation of Module contents | Availability of the draft contents for 5 modules
5 – Revision, finalization and translation of module contents | Peer review of the 5 modules and availability of in English, Italian, Romanian and Portuguese of the online training package
6 – Testing activities | Testing of the handbook with 20 childhood educators and kindergarten teachers per country (40 for Portugal) Availability of 4 national evaluation reports Availability of 1 transnational evaluation report Availability of 1 target group involvement declaration per country
WP3 - Online Training Package

## Slide 23: 1 – Planning of the activities
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) should create a working group involving in the contents creation:
  The director or a representative of the managerial staff who will ensure that the handbook contents are recognised and accepted by the kindergarten
  5 Early childhood educators who will have an active role in supporting the experts of IPB, ULS and in adapting the pedagogic and methodological contents to the specific needs of educators
  Template: WP3.M – Working Group involvement declaration
IPB (PT) and ULS (IE) should create a working group involving 4 experts/lecturers/researchers in the contents creation
Template: WP3.M - Target Group involvement declaration
Each partner should participate in the Partners’ Meeting in Bragança on:
4-5 September 2023
WP3 - Online Training Package

## Slide 24: 2 – Organisation of the Training activity
Organisation in Iasi (RO) of a training event:
Title: Pedagogical Documentation on Children's’ Learning: Leading towards a Digital Portfolio
Trainers: 3 experts from IPB (PT)
Participants: 5 kindergartner teachers from IC Sestini (IT), CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE)
Period: 3 – 7 July 2023 (training days)
Duration: 7 days (including 2 travelling days)
Certification: Europass Mobility
Templates: WP3.A – TA Programme
WP3.B – TA List of Participants
WP3.C – TA Certificates
WP3.D – Europass Contents
WP3.E – TA Report
WP3.E2 – Description of the participants (5 lines each)
WP3 - Online Training Package

## Slide 25: 3 – Definition of the online course syllabus and structure
IPB (PT) and ULS (IE) should propose the online training package syllabus and structure divided into 5 modules:
Actors involved in the Pedagogical Documentation Process
Documenting Child Daily Action
The observation of children’s action: instruments and processes
Practical aspects of documentaiton
Creating Portfolios in the Digital Portfolio Management System (DPMS)
  Templates: WP3.F – Training Package table of contents
Each partner should analyze and give feedback related to the online training package syllabus and structure
IPB (PT) and ULS (IE) should produce the final version of the online training package syllabus and structure
WP3 - Online Training Package

## Slide 26: 4 – Creation of modules contents
IPB (PT) and ULS (IE) should propose the contents of the 5 modules of the training package.
Each module should include:
Introductory text
Multimedia material (videos, presentations, audiofiles)
Bibliographic references
Case scenarios
Self-assessment evaluaiton test
  Template: WP3.G – Guidelines to develop the Training Package contents
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) should contribute to the adaptation of the training package contents to childhood education professionals and kindergartner teachers
WP3 - Online Training Package

## Slide 27: 5 - Finalization and translation of modules
IPB (PT) and ULS (IE), on the basis of the suggestions provided by the kindergartens, should produce the final version of the online training package
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) should translate the online training paclage into the national languages
WP3 - Online Training Package

## Slide 28: 6 – Testing activities and evaluation
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) should involve 20 among kindergarten teachers and earlychildhood educators in the assessment of the online training package and produce a national evaluation report.
Templates: WP2.H – Evaluation Questionnaire
WP2.I– Tool for questionnaire analysis
WP2.L – Guidelines for evaluation report
WP2.M – Target Group involvement declaration
WP3 - Online Training Package

## Slide 29
Actions and Deadlines
Action | Deadline | Status
IPB (PT) Definition for the training activity of the: Programme Contents for the Mobility Europass | 16 April 2023 | 
EuroEd (RO) Logistic organization of the training activity | 3 – 7 July 2023 | 
IPB (PT) Scientific delivery of the training activity | 3 – 7 July 2023 | 
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) Participation in the training activity with 5 kindergartner teachers | 3 – 7 July 2023 | 
IPB (PT) Sending, for the training activity, of the: Programme List of Participants Certificates Report | 31 July 2023 | 
WP3 - Online Training Package

## Slide 30
Actions and Deadlines
Action | Deadline | Status
IC Sestini (IT), CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) Sending of the Europass certificates of the participants | 31 July 2023 | 
IPB (PT), Pixel (IT) Creation of the templates needed for carrying out the activities | 30 June 2023 | 
IPB (PT), ULS (IE) Define the draft version of the table of contents of the online training package | 30 July 2023 | 
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) Provide IPB and ULS (IE) with feedback on the table of contents | 15 September 2023 | 
IPB (PT), ULS (IE) Define the final version of the table of contents of the online training package | 30 September 2023 | 
IPB (PT), ULS (IE) Each partner should produce the contents related to 1 module | 30 November 2023 | 
WP3 - Online Training Package

## Slide 31
Actions and Deadlines
Action | Deadline | Status
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) Provide IPB and ULS with feedback on the contents of the first 2 modules | 15 December 2023 | 
IPB (PT), ULS (IE) IPB produces the contents for 2 modules ULS produces the contents for 1 module | 31 January 2024 | 
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) Provide IPB and ULS with feedback on the contents of the last 3 modules | 28 February 2024 | 
IPB (PT), ULS (IE) Production of the final version of the first 2 modules | 31 March 2024 | 
IPB (PT), ULS (IE) Production of the final version of the last 3 modules | 30 April 2024 | 
WP3 - Online Training Package

## Slide 32
Actions and Deadlines
Action | Deadline | Status
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) Translation of the first 2 modules into the national languages | 15 April 2024 | 
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) Translation of the last 3 modules into the national languages | 30 June 2024 | 
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) Test of the online training package | 30 October 2024 | 
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) Collect 20 evaluation questionnaires from the representatives of the target groups Sending of the National Testing Report Send the declaration of the target groups involvemen | 30 November 2024 | 
Pixel (IT) Production of Transnational Testing Reports | 30 December 2024 | 
WP3 - Online Training Package

## Slide 33: WP4 - Digital Portfolio Management System

## Slide 34
Activities and Results
Activities | Results
1 – Planning | Availability of: Calendar of activities Templates and tools
2 – Proposal, discussion and approval of the Digital Portfolio Management System (DPMS) technical structure | 1 participant per partner in the transnational meeting Availability of the description of technical structure of the DPMS including 3 areas: managers, teachers, and families
3 – Creation of the Case studies materials | Availability of 10 case studies (2 per country, 4 for Portugal)
4 – Creation and debugging of the DPMS | Availability of the debugged section of the DPMS
5 – Uploading of the case studies on the DPMS | Availability on the DPMS of 5 exemplary case studies per country (10 for Portugal)
6 – Testing activities | Testing of the handbook with 20 childhood educators and kindergarten teachers per country (40 for Portugal) Availability of 4 national evaluation reports Availability of 1 transnational evaluation report Availability of 1 target group involvement declaration per country
WP4 - Digital Portfolio Management System

## Slide 35: 1 – Planning of the activities
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) should create a working group involving in the contents creation:
  The director or a representative of the managerial staff who will ensure that the handbook contents are recognised and accepted by the kindergarten
  5 Early childhood educators who will have an active role in supporting the experts of IPB, ULS and in adapting the pedagogic and methodological contents to the specific needs of educators
  Template: WP4.F- Target Group involvement declaration
IPB (PT) and ULS (IE) should create a working group involving 4 experts/lecturers/researchers in the contents creation
Template: WP4.F - Target Group involvement declaration
WP4 - Digital Portfolio Management System

## Slide 36: 2 – DPMS technical structure
IPB (PT) and Pixel (IT) should produce the description of technical structure of the DPMS that should:
Foresee 4 different users typologies: managers, kindergartner teachers, children , parents
Allow educators and kindergartner teachers to store, organize and present the data of the children
Templates: WP4.A - Technical structure of the DPMS
All partners should analyse and comment the technical structure of the DPMS
All partners should participate in the Partners’ Meeting in Dublin on:
???? October 2024
IPB (PT) and Pixel (IT) should produce the final version of the description of technical structure of the DPMS
WP4 - Digital Portfolio Management System

## Slide 37: 3 – Creation of the Case studies materials
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) should produce 5 exemplary case studies each documenting the progress of 5 children
  Templates: WP4.B - Case study
WP4 - Digital Portfolio Management System

## Slide 38: 4 – Creation and debugging of the DPMS
IPB (PT) and Pixel (IT) should create the Digital Portfolio Management Structure (DPMS)
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) and ULS (IE) should debug the DPMS
IPB (PT) and Pixel (IT) should create the final version of the Digital Portfolio Management Structure (DPMS)
WP4 - Digital Portfolio Management System

## Slide 39: 5 - Uploading of the case studies on the DPMS
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) and ULS (IE) should upload the produced case studies on the DPMS
IPB (PT) and Pixel (IT) should help the schools in the process
WP4 - Digital Portfolio Management System

## Slide 40: 6 – Testing activities and evaluation
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) should involve 20 among kindergarten teachers and earlychildhood educators in the assessment of the DPMS and produce a national evaluation report.
Templates: WP4.C – Evaluation Questionnaire
WP4.D – Tool for questionnaire analysis
WP4.E – Guidelines for evaluation report
WP4.F – Target Group involvement declaration
WP4 - Digital Portfolio Management System

## Slide 41
Actions and Deadlines
Action | Deadline | Status
IPB (PT), Pixel (IT) Creation of the templates needed for carrying out the activities | 30 July 2024 | 
IPB (PT), Pixel (IT) Define the draft version of the DPMS structure | 30 September 2024 | 
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) Provide feedback on the DPMS structure | 30 October 2024 | 
IPB (PT), Pixel (IT) Define the final version of the of the DPMS structure | 30 November 2024 | 
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) Collect the material for 5 case scenarios per country (10 for Portugal) | 28 February 2025 | 
WP4 - Digital Portfolio Management System

## Slide 42
Actions and Deadlines
Action | Deadline | Status
IPB (PT), Pixel (IT) Create the DPMS | 28 February 2025 | 
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) Upoad the material of the case studies on the DPMS and provide feedback on the DPMS | 30 April 2025 | 
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) Test the DPMS with 20 kindergartner teachers per country (40 for Portugal) | 30 September 2025 | 
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) Collect 20 evaluation questionnaires from the representatives of the target groups Sending of the National Testing Report Send the declaration of the target groups involvemen | 30 October 2025 | 
Pixel (IT) Production of Transnational Testing Reports | 30 November 2025 | 
WP4 - Digital Portfolio Management System

## Slide 43
WP1 – Project Management

## Slide 44: WP1 – Project Management
  Inclusion Dimension:
    Improving the outreach to people with fewer opportunities (disable people, rural areas, etc)
  Digital Dimension:
    Digital technologies in education
  Environmental Dimension:
    Memorandum of understanding
Activities - Priorities

## Slide 45: WP1 – Project Management
  Pixel is the project internal Evaluator and produces the Quality Plan.
  The Quality Plan defines:
      The procedures for the quality assessment
      The quantitative and qualitative indicators for each WP
    The Portuguese NA assessment will be based on the quality of the products and the achievements on the indicators
Activities - Quality Assurance

## Slide 46: WP1 – Project Management
Activities – Online Meetings
Participation in Online Partners’ Meetings
    December 2022 
    November 2025
Other online meetings will be agreed, if necessary, during the project lifetime

## Slide 47: WP1 – Project Management
Narrative Report
  Objectives
  Activities carried
  Results achieved
Template: Activity to be carried out directly on the project website (WP1.A)
Activities - Reporting

## Slide 48: WP1 – Project Management
Financial and Administrative Management
Templates
  WP1.B - Guidelines for financial management
  WP1.C – Templates for financial management
Activities – Financial Reporting

## Slide 49: WP1 – Project Management
Actions and Deadlines
Action | Deadline | Status
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE), IPB (PT) Send feedback on the quality plan Send feedback on the Memorandum of Understanding | 22 December 2022 | Completed
All partners Carry out the narrative activity report on the web site | Progress report 30 November 2023 | 
All partners Send the financial reports with supporting documents | Final report 30 November 2025 | 

## Slide 50
WP5 – Valorization

## Slide 51: WP5 – Valorization
Activities and Results
Activities | Results
1 – Definition of the Valorization Plan | Availability of the Communication and Valorisation Plan
2 – Creation and sharing of the Dissemination package | Availability of: Project logo Project brochure in all languages Templates for associated partners Dissemination and sustainability sections on the website Project summary
3 – Implementation of the dissemination and exploitation activities | Availability of the database of dissemination events filled in with at least 175 dissemination events Availability of 36 associated partners on the project website Availability of 42 links, articles and web articles on the website
4 – Organisation of the Multiplier events | Organization of 1 event per country (3 for Portugal) involving at least 40 participants among early childhood educators and kindergarten teachers, decision-makers, policymakers and experts.
5 – Assessment of the activities | Assessment of the dissemination events in the database
6 – Evaluation and Reporting | Availability of the Valorisation Report

## Slide 52: WP5 – Valorization
1 – Definition of the Valorization Plan
  The Valorization plan refers to internal communication, the dissemination and exploitation activities and defines:
    Objectives
    Target Groups
    Subjects in charge
    Contents
    Strategies
    Activities

## Slide 53
  The dissemination package includes:
    Project logo
    Project brochure
    Templates for associated partners
    Dissemination and sustainability sections on the website
    Project summary
2 - Dissemination package
WP5 – Valorization
“Open Educational Resources (OER) are teaching, learning and research materials in any medium – digital or otherwise – that reside in the public domain or have been released under an open license that permits no-cost access, use, adaptation and redistribution by others with no or limited restrictions.”

## Slide 54: WP5 – Valorization
  Each partner should carry out at least 36 dissemination events (an average of 1 event per month. The events include:
    Training seminars
    Transnational Meetings
    National Meetings
    Article in newspapers
    Articles in magazines
    Conferences or Fairs
    Newsletters
    Articles on websites
    Informative Mailings
3 – Dissemination and exploitation activities

## Slide 55: WP5 – Valorization
  Each partner should involve in the project at least 6 associated partners.
  Templates:
  WP5.B – Associated Partner Letter
  WP5.C – Associated Partner Form
  Each partner should produce at least 7 among exchange links, articles or web articles related to the project
  Templates:
  WP5.D – Links
  WP5.E – Articles
3 – Dissemination and exploitation activities

## Slide 56: WP5 – Valorization
  Organisation of 6 events (1 per country, 3 for Portugal) involving at least 40 participants in each event.
  The participants should be stakeholders representatives
  Templates:
  WP5.F – Description
  WP5.G – Programme
  WP5.H – List of Participants
4 – Organisation of the Multiplier events

## Slide 57: WP5 – Valorization
  Each partner should upload on the project website the description and assessment of the carried out dissemination activities
  The events should be uploaded on the database (WP5.A) available on the project website
5 – Assessment of the activities

## Slide 58: WP5 – Valorization
  Each partner should produce a Sustainability Report
  Templates:
  WP5.I – Best Practice Dissemination Report
  WP5.L – Sustainability Report
  Pixel should produce the Transnational Valorization and Sustainability Report
6 – Evaluation and Reporting

## Slide 59: WP5 – Valorization
Actions and Deadlines
Action | Deadline | Status
IPB (PT) Development of project brochure | 10 March 2023 | 
All Partners Post of a link to the project portal on each one of the partners’ organizations websites | 31 March 2023 | 
All Partners Translation of project brochure in the national language | 15 March 2023 | 
All Partners Upload at least 3 dissemination events | 31 March 2023 | 
All Partners Organization of 1 dissemination event on the project every month and uploading the information on the project web site | 28 February, 30 May, August, November 2023 28 February, 30 May, August, November 2024 28 February, 30 May, August, November 2025 | 

## Slide 60: WP5 – Valorization
Actions and Deadlines
Action | Deadline | Status
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE), IPB (PT) Involvement as associated partners of at least 3 organizations operating in the field of the project. | Progress Report | 
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE), IPB (PT) Publication of at least 3 among exchange links, articles or web articles | Progress Report | 
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE), IPB (PT) Involvement as associated partners of at least 6 organizations operating in the field of the project. | 15 November 2025 | 
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE), IPB (PT) Publication of at least 7 among exchange links, articles or web articles | 15 November 2025 | 

## Slide 61: WP5 – Valorization
Actions and Deadlines
Action | Deadline | Status
IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE), IPB (PT) Sending of the document related to the organized Events with 40 participants | 15 November 2025 | 
All Partners Sending of the Sustainability Report Sending of the Best Practice Dissemination Report | 15 November 2025 | 
Pixel (IT) Production of the transnational Valorization report | 30 November 2025 | 

## Slide 62: Thanks!
Any questions?