**Calendar of Deadlines**

**WP1: Management**

|  |  |  |  |
| --- | --- | --- | --- |
| **Deadline** | **Results**  | **Partner** | **Template and Tools** |
| Progress reportFinal report: 30 November 2025 | Carry out the narrative activity report on the web site | All partners | WP1.B - Activity to be carried out directly on the project website |
| Progress reportFinal report:31 October 2025 | Financial report | All partners | WP1.C - Guidelines for financial managementWP1.D - Templates for financial management |

 **WP2 – Handbook**

|  |  |  |  |
| --- | --- | --- | --- |
| **Deadline** | **Results**  | **Partner** | **Template and Tools** |
| 16 March 2023 | Production of the national needs analysis reports | IPB (PT) | WP2.B – Table of contents for national reportsWP2.C – Guidelines for the national report production |
| 16 March 2023 | Provide IPB and ULS with examples of National policy requirements and suggestions for participatory pedagogies | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) | WP2.D – Table of Contents for Handbook |
| 20 March 2023 | Send 4 needs analysis reports with the final layout. | IPB (PT) |  |
| 31 March 2023 | Definition of the final version of the table of contents for the handbook | IPB (PT), ULS (IE) |  |
| 14 April 2023 | Production of Transnational Needs Analysis Report. | IPB (PT) |  |
| 15 June 2023 | Definition of the draft version of the contents for the handbook | IPB (PT), ULS (IE) | WP2.D – Table of Contents for HandbookWP2.E – Guidelines for the Handbook production |
| 30 June 2023 | Send feedback related to the contents of the handbook | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) | WP2.D – Table of Contents for HandbookWP2.E – Guidelines for the Handbook production |
| 31 July 2023 | Definition of the final version of the contents for the handbook | IPB (PT), ULS (IE) | WP2.D – Table of Contents for HandbookWP2.E – Guidelines for the Handbook production |
| 30 September 2023 | Translation of the handbook in the national language | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) |  |
| 31 December 2023 | Send letter of involvement of target groups | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE), IPB (PT) | WP1.A - Target Group involvement declaration |
| 31 December 2023 | Collect 20 evaluation questionnaires from the representatives of the target groupsSending of the National Testing Report | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) | WP2.F – Evaluation QuestionnaireWP2.G – Tool for questionnaire analysisWP2.H – Guidelines for evaluation report |
| 31 January 2024 | Production of transnational evaluation report | Pixel (IT) | WP2.H – Guidelines for evaluation report |

**WP3 - Online Training Package**

|  |  |  |  |
| --- | --- | --- | --- |
| **Deadline** | **Results**  | **Partner** | **Template and Tools** |
| 16 April 2023 | Definition for the training activity of the:* Programme
* Contents for the Mobility Europass
 | IPB (PT) | WP3.A – TA ProgrammeWP3.D – Europass Contents |
| 30 June 2023 | Creation of the templates needed for carrying out the activities | IPB (PT), Pixel (IT) |  |
| 3 – 7 July 2023 | Logistic organization of the training activity | EuroEd (RO) |  |
| 3 – 7 July 2023 | Scientific delivery of the training activity | IPB (PT) |  |
| 3 – 7 July 2023 | Participation in the training activity with 5 kindergartner teachers | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) | WP3.E2 – Description of the participants (5 lines each) |
| 31 July 2023 | Sending, for the training activity, of the:* Programme
* List of Participants
* Certificates
* Report
 | IPB (PT) | WP3.A – TA ProgrammeWP3.B – TA List of ParticipantsWP3.C – TA CertificatesWP3.E – TA Report |
| 31 July 2023 | Sending of the Europass certificates of the participants | IC Sestini (IT), CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) | WP3.D – Europass Contents |
| 31 July 2023 | Define the draft version of the table of contents of the online training package | IPB (PT), ULS (IE) | WP3.F – Training Package table of contents |
| 15 September 2023 | Provide IPB and ULS (IE) with feedback on the table of contents | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) | WP3.F – Training Package table of contents |
| 30 September 2023 | Define the final version of the table of contents of the online training package | IPB (PT), ULS (IE) | WP3.F – Training Package table of contents |
| 30 November 2023 | Each partner should produce the contents related to 1 module | IPB (PT), ULS (IE) | WP3.G – Guidelines to develop the Training Package contents |
| 15 December 2023 | Provide IPB and ULS with feedback on the contents of the first 2 modules | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) | WP3.G – Guidelines to develop the Training Package contents |
| 31 January 2024 | IPB produces the contents for 2 modulesULS produces the contents for 1 module | IPB (PT), ULS (IE) | WP3.G – Guidelines to develop the Training Package contents |
| 28 February 2024 | Provide IPB and ULS with feedback on the contents of the last 3 modules | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) | WP3.G – Guidelines to develop the Training Package contents |
| 31 March 2024 | Production of the final version of the first 2 modules | IPB (PT), ULS (IE) | WP3.G – Guidelines to develop the Training Package contents |
| 30 April 2024 | Production of the final version of the last 3 modules | IPB (PT), ULS (IE) | WP3.G – Guidelines to develop the Training Package contents |
| 15 April 2024 | Translation of the first 2 modules into the national languages | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) |  |
| 30 June 2024 | Translation of the last 3 modules into the national languages | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) |  |
| 30 October 2024 | Test of the online training package | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) |  |
| 30 November 2024 | Collect 20 evaluation questionnaires from the representatives of the target groupsSending of the National Testing ReportSend the declaration of the target groups involvement | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) | WP2.H – Evaluation QuestionnaireWP2.I– Tool for questionnaire analysisWP2.L – Guidelines for evaluation reportWP2.M – Target Group involvement declaration |
| 30 December 2024 | Production of Transnational Testing Reports | Pixel (IT) |  |

**WP4 – Digital Portfolio Management System**

|  |  |  |  |
| --- | --- | --- | --- |
| **Deadline** | **Results**  | **Partner** | **Template and Tools** |
| 30 July 2024 | Creation of the templates needed for carrying out the activities | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) |  |
| 30 September 2024 | Define the draft version of the DPMS structure | IPB (PT), Pixel (IT) | WP4.A - Technical structure of the DPMS |
| 30 October 2024  | Provide feedback on the DPMS structure | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO) | WP4.A - Technical structure of the DPMS |
| 30 November 2024 | Define the final version of the of the DPMS structure | IPB (PT), Pixel (IT) | WP4.A - Technical structure of the DPMS |
| 28 February 2025 | Collect the material for 5 case scenarios per country (10 for Portugal) | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) | WP4.B - Case study |
| 28 February 2025 | Create the DPMS | IPB (PT), Pixel (IT) |  |
| 30 April 2025 | Upload the material of the case studies on the DPMS and provide feedback on the DPMS | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) | WP4.A - Technical structure of the DPMS |
| 30 September 2025 | Test the DPMS with 20 kindergartner teachers per country (40 for Portugal) | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) | WP2.C – Evaluation QuestionnaireWP2.D – Tool for questionnaire analysisWP2.E – Guidelines for evaluation reportWP4.I - Target Group involvement declaration |
| 30 October 2025 | Collect 20 evaluation questionnaires from the representatives of the target groupsSending of the National Testing ReportSend the declaration of the target groups involvement | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE) | WP4.C – Evaluation QuestionnaireWP4.D – Tool for questionnaire analysisWP4.E – Guidelines for evaluation reportWP4.F - Target Group involvement declaration |
| 30 November 2025 | Production of Transnational Testing Reports | Pixel (IT) |  |

**WP5 – Valorization**

|  |  |  |  |
| --- | --- | --- | --- |
| **Deadline** | **Results**  | **Partner** | **Template and Tools** |
| 10 March 2023 | Development of project brochure | IPB (PT) |  |
| 31 March 2023 | Post of a link to the project portal on each one of the partners’ organizations websites | All partners | WP5.D - Links |
| 15 March 2023 | Translation of project brochure in the national language | All partners |  |
| 28 February, 30 May, August, November 202328 February, 30 May, August, November 202428 February, 30 May, August, November 2025 | Organization of 1 dissemination event on the project every month and uploading the information on the project web site  | All partners | WP5.A - Dissemination Activities (Link to be added) |
| Progress report | Involvement as associated partners of at least 3 organization operating in the field of the project. | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE), IPB (PT) | WP5.B - Associated Partner LetterWP5.C - Associated Partner Form |
| Progress report | Publication of at least 3 among exchange links, articles or web articles | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE), IPB (PT) | WP5.D - LinksWP5.E - Articles |
| 15 November 2025 | Involvement as associated partners of at least 6 organizations operating in the field of the project | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE), IPB (PT) | WP5.B - Associated Partner LetterWP5.C - Associated Partner Form |
| 15 November 2025 | Publication of at least 7 among exchange links, articles or web articles | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE), IPB (PT) | WP5.D - LinksWP5.E - Articles |
| 15 November 2025 | Sending of the document related to the organized Events with 40 participants | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE), IPB (PT) | WP5.F - DescriptionWP5.G - ProgrammeWP5.H - List of Participants |
| 15 November 2025 | Sending of the Sustainability Report and Best Practice Dissemination Report | IC Sestini (IT) CSSanta Clara (PT), AE Miguel Torga (PT), EuroEd (RO), ULS (IE), IPB (PT) | WP5.I – Best Practice Dissemination ReportWP5.L – Sustainability Report |
| 30 November 2025 | Production of the transnational valorisation report  | Pixel (IT) |  |