## Slide 1: EYDP: Early Years Digital Portfolio
Administrative Management and Reporting Process
Project number
2022-1-PT01-KA220-SCH-000086979

## Slide 2: Main Reference Documents
The most important documents concerning financial management are:
  The Agreement with the National Agency
  The Administrative and Contractual Provisions
  The Agreement between the Applicant and the Project partner
  The Key Action 2 Partnerships for Cooperation Handbook on the lump sum funding model

## Slide 3: General principles

## Slide 4: Funding Model
The budget and reporting process of Erasmus+ KA2 Cooperation Partnership is based on the Lump Sum funding Model.
The Grant will take the form of one single fixed amount (single lump sum), covering all costs of eligible activities linked to the implementation of the project.

## Slide 5: Co-financing and No-profit
Contributions shall comply with the principles of co-financing and no-profit.
The principle of co-financing implies that the resources necessary to carry out the action are not provided entirely by the grant.
In line with the no-profit principle Grants shall not have the purpose or effect of producing a profit within the framework of the action or the work programme of the beneficiary.

## Slide 6: Activities covered by the Lump Sum
The Lump Sum shall be used to cover all costs related to the implementation of eligible activities:
Project management and coordination
Learning, Teaching and Training activities
Meetings and Events
Project deliverables
Activities aimed at sharing project’s results

## Slide 7: Costs covered by the Lump Sum
Typical costs linked to such activities would be: travel and subsistence; equipment; costs for publication and editing of materials; IT development (such as creating a website); staff and human resources costs; administrative costs; etc.
ATTENTION!!! Use of Subcontracting needs to be always communicated to the Applicant in order to promptly inform the National Agency.

## Slide 8: Budget
The budget is structured according to the 5 workpackages in which the project Workplan is organised.
Each Workpackage is assigned its own Lump Sum amount.

## Slide 9: Budget Management
Once the grant is awarded, beneficiaries have flexibility in the management of the budget allocated to each work package.
At reporting stage, the amount paid for each work package stays the same as the one approved and only depends on the level of achievement of the objectives of the work package itself.

## Slide 10: Level of Achievement
Work Packages description includes references to the specific objectives, illustrates the activities and deliverables to be produced and shows how these contribute to the achievement of the objectives.
The description is supported by a system of quantitative and qualitative indicators enabling to assess the performance of the project and the relevance of each activity.
ATTENTION!!! The Quality Plan provides all relevant information on the matter.

## Slide 11: Reporting and assessment

## Slide 12: Reporting
The assessment of the interim and final reports is made, by the experts evaluators, according to the same award criteria used to evaluate the project proposal at selection stage.
The overall structure of the report addresses:
Project management
Project implementation
Dissemination and impact

## Slide 13: Reporting Tool *
* Source Key Action 2 Partnerships for Cooperation Handbook on the lump sum funding model

## Slide 14: Reporting Score
Each work package is evaluated separately and receives a separate score.
The overall project score is calculated as the weighted average of the scores for each work package.
The Grant is paid according to the Score following this table:
ATTENTION!!! If the overall project score is sufficient but the score of one or more work packages is not, a specific grant reduction will be applied, based on the same scale.

## Slide 15: Checks and Audits
Check and Audits are aimed at verifying the correct implementation of the project activities as well as the achievement of the expected results and the production of the foreseen outputs according to the indicators.
Documentation providing evidence of the above might be requested.

## Slide 16: Reporting process and Documentary evidences

## Slide 17: Reporting Deadlines
Report | Deadline
1st Progress Report | 1 November 2023
2nd Progress Report | 1 March 2024
Final Report | 30 November 2025

## Slide 18: Reporting Approach
At reporting stage beneficiaries are requested to :
For project management: describe aspects related to the cooperation among partners, working arrangements, distribution of tasks and coordination, respect of project timeline.
For WP 2 to WP 5: provide quantitative and qualitative evidence of results obtained with the indicators and with the expected results stated in the application.
For dissemination and impact: show how the results of the projects were made available and produced benefits for other stakeholders.
Reference documents: Quality Plan + Reporting tool

## Slide 19: Reporting Process 1/3
It is needed to provide full description of how resources were used by filling the Report form providing details about:
Activities undertaken
Results achieved
Indicators met
Self assessment of the performance (1 - 100)

## Slide 20: Reporting Process 2/3
The description of activities and results must be detailed and shall include reference to the related indicators, relevant evidences and supporting documents.

## Slide 21: Reporting Process 3/3
It is requested to collect and provide necessary documentary evidence of the performed activities and the achievement of reported results.

## Slide 22: Reporting Evidences 1/4
Documentary evidences for the results / outputs are listed in the internal reporting tool together with the related quantitative / qualitative indicators, when relevant.

## Slide 23: Reporting Evidences 2/4
Staff
As supplementary evidences (recommended by National Agencies) to assess the project activities implementation we request to prepare and send:
Staff Declaration
Time Cards

## Slide 24: Reporting Evidences 3/4
Meetings
As supplementary evidences (recommended by National Agencies) to assess the project activities implementation we request to collect and send at reporting stage:
Attendance certificate
Proof of travel (e.g. flight / train ticket, boarding cards)
Hotel invoice

## Slide 25: Reporting Documents 4/4
Events / Training activities / Testing
As supplementary evidences (recommended by National Agencies) to assess the project activities implementation we request to collect and send at reporting stage:
List of participants with signatures
Programme
Report

## Slide 26: Supporting Documents
Supporting documents must be enclosed to the Report.
Only copies/scansion of supporting documents should be sent.
All original documents must be kept five years from the date of final payment.

## Slide 27: Administrative and financial Management

## Slide 28: Eligible Costs
Costs are eligible according to the rules as:
Incurred within the implementation period: 1 December 2022 – 30 November 2025
Indicated in the estimated budget of the action
Incurred in connection with the action and necessary for its implementation
Being identifiable and verifiable
Complying with the requirements of applicable tax and social legislation
Being reasonable, justified and comply with the principle of sound financial management, in particular regarding economy and efficiency

## Slide 29: Accountancy
All costs and transactions must be registered systematically in the beneficiary’s internal accounting records and determined according to the applicable accounting standards of the country where the beneficiary is established and according to the beneficiary’s usual cost accounting practices.

## Slide 30: Instalments
Instalments | % of Grant | Conditions
1st payment | 40 % | Signature of the contract and annexes Payment by the NA of the 1st instalment to the Applicant
2nd payment | 40 % | Co-beneficiary progress report approved by the Applicant Approval of the Progress report by the NA Payment by the NA of the 2nd instalment to the Applicant
3rd payment | 20 % * | Final assessment by the NA Payment by the NA of the final instalment to the Applicant
* The calculation of the final instalment will be reviewed according to the final assessment by the National Agency of the Final Report and Grant.

## Slide 31: Final Reminder

## Slide 32: Reporting Deadlines
Report | Deadline
1st Progress Report | 1 November 2023
2nd Progress Report | 1 March 2024
Final Report | 30 November 2025
Each report includes: Report form (see model) duly filled in + Supporting documents (copies/scansion) including: Staff: Staff declaration + Time Cards Meetings: Attendance certificate + Boarding cards + Hotel invoice Events / Training / Testing: List of participants with signatures + Programme + Report | 

## Slide 33: Thanks!
Any questions?
andrea@pixel-online.net